## Sheet1
Bug Report for ePharmacy mobile application
Bug ID | Bug Title | Bug Description | Pre-requisites | Bug repro-steps | Bug(Actual Result) | Expected Result | Attachment | Priority | Severity | Environment | Status
Bug_ID_01+A5:K11 | Bug occurs while generating OTP | Application takes a long time to generate OTP hence user get OTP expire error | User should be on home page | 1.Click on login 2.click on forget password 3.Enter Email in the field 4.click on continue | Application takes a long time to generate OTP | Application Should generate OTP Just in Sec after clicking Continue button | Bug_ID_01 | high | major | Android 10
Bug_ID_02 | Typo bug in password suggestion | User is not able to undertand sentence because of typo bug | User should be on home page | 1.Click on login 2.click on forget password 3.Enter Invalid Email in the field 4. click on Continue | Typo bug in "Aplha" word | "Aplha" word should be written as "Alpha" | Bug_ID_02 | high | cosmetic | Android 10
Bug_ID_03 | Bug in Facebook sign in | User is not able to sign in using facebook, it shows spinning wheel | User should be on home page | 1.Click on login 2.click on facebook | Clicking on facebook,it show Spinning wheel and never finish loading | user should sign in using facebook | Bug_ID_03 | high | major | Android 10
Bug_ID_04 | Bug in Wishlist icon | User is not able to see Wishlist on home page | User should be on home page | 1. Click on home icon | Wishlist icon is available | Wishlist icon should be on home page | Bug_ID_04 | medium | major | Android 10
Bug_ID_05 | Bug in Odered product page | User can't cancel odered product | User should be odered the product | 1.Click on Upper right circle icon 2.click on orders icon | Cancel the Ordered product button not present | User should able to cancel the odered product | Bug_ID_05 | high | major | Android 10
Bug_ID_06 | Bug in package count notification | User is not able to see any notification number on package icon when user create package | User should be on home page | 1.Click on Package icon | Number notification is not displayed on package icon | Number notification should be displayed on package icon | Bug_ID_06 | medium | Major | Android 10
Bug_ID_07 | Bug in "Refer a Friend" Button | after entering 10 digit no in mobile no text field by a user it's show an error | User should be on home page | 1. scroll down screen 2.Click on "Refer a friend button" 3. Enter mobile no in text field 4.Click on refer | Error"Invalid mobile no" occurs after entering 10 digit | refer a friend should be done | Bug_ID_07 | medium | major | Android 10
Bug_ID_08 | Bug in Tags filter | User is not able to find any details on tags page | User should be on home page | 1.click on any categories 2.click on filter 3.click on tags | Bank page is open | Tags page detail should be shown | Bug_ID_08 | high | Major | Android 10
Bug_ID_09 | Bug in Review | Application is not updated the review | User should be on home page | 1.click on any personal care Catergories 2.Click on Any product 3.click on write a Review 4.Tap on star 5.Enter Short title in Text Field 6.Enter the description | Written review is not updated | written review should be updated | Bug_ID_09 | high | major | Android 11
Bug_ID_10 | Bug in package detail product | User is not able to find product detail after clicking on product | User should be created a package and should be on home page | 1.click on any personal care Catergories 2.add product into package 3.click on package icon | product details is not showing | Product details should be shown | Bug_ID_10 | Medium | major | Android 11
Bug_ID_11 | Bug in policies options page | About us , privacy policy, shipping returns, term conditions written text are in align | user should be on setting page | 1.click on policies 2.Click on About us, privacy policy, shipping returns, term conditions | Text alignment is not proper | Text alignment should be proper | Bug_ID_11 | low | low | Android10
Bug_ID_12 | Bug in Promo notification page | Page of notification of promo is open on web browser insist of mobile application | User should be on home page | 1. Click on notification icon 2.click on promo 3. click notification of promo | nava barosa ko harsh, valentines, year end, tihar festival,dashain festive pages are open on web browser | all pages should be open on mobile application | Bug_ID_12 | medium | major | Android10
Bug_ID_13 | Bug in weight field | user can give input only two digit no in this field | User should be on home page | 1.Click on Upper right circle icon 2.click on profile 3. click on health 4.click on weight 5.Enter three digit no | three digit no can't accept, it convert three digit no into decimal no | weight input value should be three digit no | Bug_ID_13 | high | major | Android10
Bug_ID_14 | Bug in Notification page | Users are not able to find out proper sequence of Date in notification page | User should be on home page | 1.Click on notification icon 2.scroll down notification page | Date of notification is inappropriate | Date of notification should be in odered | Bug_ID_14 | high | major | Android10
Bug_ID_15 | Bug in Nofication page | Users are seeing same repeated notification | User should be on home page | 1.Click on notification icon 2.scroll down notification page | Repetation of same notifications | same Notification should not be repeated | Bug_ID_15 | medium | minor | Android10
Bug_ID_16 | Bug in UPLOAD PRESCRIPTION button | User is not able to upload the prescription in UPLOAD PRESCRIPTION option | User should be on home page | 1.click on "UPLOAD PRESCRIPTION" button | while clicking "UPLOAD PRESCRIPTION" button, entering mobilr text field open | Prescription should be uploaded | Bug_ID_16 | high | minor | Android10
Bug_ID_17 | bug in Add product "Plus - minus" button | after a product limit max 100 ,User is able to add product more than 100 | User should be on home page | 1.click on any personal care Catergories 2.Click on Any product details 3.enter the any no more than 200 4. Click on plus button | Plus button is add the product more than 100 | limit of adding products should be max 100 | Bug_ID_17 | medium | minor | Android10